## Worksheet
Task | Owner | Scheduled Dates |  |  | Status | Notes
|  | Start Date | End Date | Deadline
Project Proposal Drafting | John Smith | 2024-04-01 | 2024-04-10 | 2024-04-15 | In Progress | Needs client feedback by April 12.
Team Training Session | Sarah Lee | 2024-04-05 | 2024-04-05 | 2024-04-10 | Planned | All team members required.
Budget Finalization | Michael Brown | 2024-04-11 | 2024-04-18 | 2024-04-25 | Pending Approval | Submission to CFO due April 19.
Client Presentation Prep | Emily Davis | 2024-04-15 | 2024-04-20 | 2024-04-23 | Not Started | Presentation materials to be finalized by April 18.
Project Kickoff Meeting | David Wilson | 2024-04-25 | 2024-04-25 | 2024-05-01 | Confirmed | All stakeholders invited.
Schedule Planner – Task Scheduling (Printable Version)