## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Progress (%) | Notes
TSK-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-03 | High | Completed | 100% | All stakeholders confirmed.
TSK-002 | Market Research Survey | Mike Johnson | 2024-04-04 | 2024-04-10 | Medium | In Progress | 60% | Data collection phase ongoing.
TSK-003 | Development Phase Kickoff | Sarah Lee | 2024-04-11 | 2024-04-20 | High | Planned | 0% | Awaiting final approval from legal team.
TSK-004 | User Testing Sessions | David Chen | 2024-04-21 | 2024-04-28 | Low | Not Started | 0% | Testing environment ready.
TSK-005 | Final Report Compilation | Lisa Wong | 2024-04-30 | 2024-05-03 | High | Completed | 100% | Delivered to executive committee.