## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Notes
T001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | 1 | High | Completed | Finalize project scope and team roles.
T002 | Market Research Analysis | Jane Smith | 2024-04-03 | 2024-04-10 | 8 | Medium | In Progress | Gather and analyze customer feedback data.
T003 | UI/UX Design Finalization | Alex Brown | 2024-04-11 | 2024-04-20 | 10 | High | Planned | Finalize wireframes and user flows.
T004 | Development Phase Start | Sam Lee | 2024-04-21 | 2024-05-15 | 35 | Critical | Scheduled | Begin coding and backend integration.
T005 | Testing & QA Review | Taylor Kim | 2024-05-16 | 2024-05-31 | 16 | High | Scheduled | Conduct full system testing and bug fixes.