## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Status
Project Planning | 2024-04-01 | 2024-04-05 | 5 | High | In Progress
Requirement Gathering | 2024-04-06 | 2024-04-15 | 10 | Medium | Not Started
Design Phase | 2024-04-16 | 2024-04-25 | 10 | High | Planned
Development Phase | 2024-04-26 | 2024-05-30 | 35 | High | Not Started
Testing & QA | 2024-06-01 | 2024-06-15 | 15 | Medium | Planned
Deployment & Launch | 2024-06-16 | 2024-06-20 | 5 | Low | Not Started