## Worksheet
Task | Assigned To | Start Date | End Date | Duration (Days) | Status | Priority
Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | 1 | Completed | High
Requirement Gathering | Jane Smith | 2024-04-02 | 2024-04-10 | 9 | In Progress | High
Design Phase Review | Mike Johnson | 2024-04-11 | 2024-04-15 | 5 | Not Started | Medium
Development Sprint 1 | Team A | 2024-04-16 | 2024-04-25 | 10 | Not Started | High
Testing & QA Review | Lisa Brown | 2024-04-26 | 2024-05-03 | 8 | Planned | Medium
Final Deployment & Handover | Admin Team | 2024-05-04 | 2024-05-05 | 2 | Not Started | High