## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Notes
T-001 | Project Kickoff Meeting | Team Lead | 2024-04-01 | 2024-04-01 | 1 | High | Completed | None | All team members to confirm attendance.
T-002 | Requirements Gathering | Product Owner | 2024-04-02 | 2024-04-10 | 9 | High | In Progress | T-001 | Finalize user stories and acceptance criteria.
T-003 | UI/UX Design Phase | Design Team | 2024-04-11 | 2024-04-25 | 15 | Medium | Planned | T-002 | Deliver wireframes and prototypes.
T-004 | Development Sprint 1 | Engineering Team | 2024-04-26 | 2024-05-03 | 8 | High | Planned | T-003 | Complete core functionality.
T-005 | Testing & QA | QA Team | 2024-05-04 | 2024-05-15 | 12 | High | Planned | T-004 | Bug fixes and regression testing.
T-006 | User Training Sessions | Customer Support | 2024-05-16 | 2024-05-18 | 3 | Medium | Planned | T-005 | Conduct sessions for end users.