## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Progress (%) | Notes
T001 | Project Planning Phase | Jane Smith | 2024-04-01 | 2024-04-15 | In Progress | Middle | 65% | Finalize scope and milestones.
T002 | User Requirements Gathering | John Doe | 2024-04-16 | 2024-05-10 | Pending | High | 20% | Initial interviews with stakeholders.
T003 | UI/UX Design Review | Sarah Lee | 2024-05-11 | 2024-05-31 | Scheduled | Medium | 0% | Design approval required from PM.
T004 | Development Phase Start | Mike Chen | 2024-06-01 | 2024-08-31 | Not Started | High | 0% | Team setup and environment provisioning.