## Worksheet
Task ID | Task Name | Priority | Due Date | Assigned To | Status | Estimated Time (hrs) | Dependencies | Notes
T001 | Review Project Timeline | High | 2023-10-15 | Jane Smith | Pending | 2.5 | None | Ensure alignment with client expectations.
T002 | Design UI Mockups | High | 2023-10-20 | Alex Johnson | In Progress | 8 | T001 | Include responsive design for mobile.
T003 | Develop Backend API | Medium | 2023-11-05 | Mike Chen | Not Started | 12 | T002 | Integrate authentication module.
T004 | Conduct User Testing | Low | 2023-11-15 | Sarah Lee | Planned | 4.5 | T002, T003 | Gather feedback for iterative improvements.
T005 | Finalize Documentation | Medium | 2023-11-25 | Lisa Wang | Not Started | 3 | T004 | Include setup guide and API reference.