## Worksheet
Task ID | Task Description | Scheduled Date | Assigned To | Priority Level | Status | Estimated Time (hrs) | Dependencies | Notes
TS-001 | Review project timeline and adjust milestones | 2023-10-15 | Sarah Chen | High | In Progress | 4 | TS-002, TS-003 | Ensure alignment with client deadlines.
TS-002 | Finalize budget proposal for Q4 | 2023-10-18 | James Reed | Medium | Pending | 3.5 | TS-001, TS-004 | Include contingency funds.
TS-003 | Conduct stakeholder meeting on product roadmap | 2023-10-20 | Lena Patel | High | Not Started | 2 | TS-001 | Invite all department leads.
TS-004 | Update project management software with new templates | 2023-10-25 | David Kim | Low | Planned | 1.5 |  | Ensure compatibility with existing tools.