## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Resources Required | Dependencies | Notes
TSK-001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-03 | High | Pending | Room Booking, Laptop, Presentation Materials | None | Initial planning session to align stakeholders.
TSK-002 | Design Phase Completion | John Smith | 2024-04-05 | 2024-04-15 | Medium | In Progress | Design Software, Team Access, Feedback Tools | TSK-001 | Finalize wireframes and UI mockups.
TSK-003 | Development Environment Setup | Alex Brown | 2024-04-16 | 2024-04-25 | Low | Not Started | Server Access, Development Tools, Version Control | TSK-002 | Configure CI/CD pipelines and local environments.
TSK-004 | User Testing Phase | Lisa Chen | 2024-05-01 | 2024-05-10 | High | Scheduled | Test Devices, Feedback Forms, QA Team | TSK-003 | Gather user feedback on prototypes.