## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Resources Required | Dependencies
T-001 | System Migration Setup | Jane Doe | 2024-04-01 | 2024-04-15 | High | In Progress | Server A, Network Team | None
T-002 | Database Backup & Verification | John Smith | 2024-04-05 | 2024-04-10 | Medium | Completed | Backup Servers, DB Admins | T-001
T-003 | Security Audit Implementation | Lisa Chen | 2024-04-12 | 2024-04-25 | High | Pending | Security Tools, IT Team | T-002
T-004 | User Training Sessions | Mark Lee | 2024-05-01 | 2024-05-15 | Low | Planned | Training Materials, Facilitator | T-003