## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status
T001 | Design Project Proposal | Jane Smith | 2024-03-15 | 2024-03-25 | High | Pending
T002 | Develop UI Mockups | John Doe | 2024-03-18 | 2024-03-28 | Medium | In Progress
T003 | Finalize Backend API | Lisa Chen | 2024-03-20 | 2024-04-10 | High | Not Started
T004 | Conduct User Testing | Mike Taylor | 2024-04-01 | 2024-04-15 | Medium | Planned