## Worksheet
Task ID | Task Name | Scheduled Date | Due Date | Responsible Person | Resource Required | Priority Level | Status
T001 | Project Kickoff Meeting | 2024-04-15 | 2024-04-15 | Jane Doe | Meeting Room, Video Conferencing Setup | High | Completed
T002 | <1th style="text-align:left;">Design Phase Review2024-04-20 | 2024-05-10 | John Smith | Design Software, 3 Designers | Medium | In Progress
T003 | Development Start | 2024-05-15 | 2024-06-30 | Alex Johnson | Development Team, Servers, APIs | High | Planned
T004 | QA Testing Phase | 2024-07-10 | 2024-07-31 | Sara Lee | QA Team, Test Environment | Medium | Not Started
T005 | Client Presentation | 2024-08-15 | 2024-08-18 | Mike Turner | Presentation Tools, 1 Hour Meeting Room | High | Scheduled