## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Assigned To | Priority Level | Status | Dependencies
TSK-001 | System Backup Setup | 2024-04-01 | 2024-04-03 | Jane Doe | High | In Progress | None
TSK-002 | Network Security Audit | 2024-04-05 | 2024-04-10 | John Smith | Critical | Pending | TSK-001
TSK-003 | User Training Workshop | 2024-04-15 | 2024-04-17 | Lisa Chen | Medium | Planned | None
TSK-004 | Cloud Migration Planning | 2024-04-20 | 2024-05-10 | Mike Turner | High | Not Started | TSK-002, TSK-003