## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Responsible Person | Priority Level | Resource Required | Status | Notes
TSK-001 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | Jane Smith | High | Meeting Room, Laptop, Project Charter | Completed | Initial planning session conducted.
TSK-002 | Design Phase Review | 2024-04-01 | 2024-04-15 | Michael Brown | Medium | Design Tools, Access to Prototypes | In Progress | Feedback from stakeholders scheduled for April 10.
TSK-003 | Development Environment Setup | 2024-04-20 | 2024-05-10 | Sarah Lee | Low | Development Servers, APIs, Cloud Access | Pending | Waiting on IT team approval.
TSK-004 | QA Testing Phase | 2024-05-15 | 2024-06-15 | David Wong | High | Test Cases, Test Environment, QA Tools | Not Started | Final version of design approved on April 30.
TSK-005 | Client Presentation | 2024-07-10 | 2024-07-12 | Lisa Chen | High | Presenter, Presentation Deck, Demo Environment | Planned | Client feedback session scheduled post-presentation.