## Worksheet
Task ID | Task Name | Scheduled Start Date | Scheduled End Date | Assigned To | Priority Level | Status | Resource Required
TSK-001 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | John Smith | High | Planned | Meeting Room, Chair, Project Manager
TSK-002 | Requirements Gathering | 2024-04-03 | 2024-04-15 | Sarah Lee | High | In Progress | Stakeholder Interviews, Documentation Tools
TSK-003 | Design Phase Review | 2024-05-10 | 2024-05-15 | Mike Johnson | Medium | Scheduled | Design Team, Sketching Tools
TSK-004 | Development Phase Start | 2024-06-01 | 2024-07-31 | Lisa Wong | High | Planned | Development Team, Servers, APIs
TSK-005 | User Testing & Feedback | 2024-08-15 | 2024-08-31 | David Brown | Medium | Pending | Test Users, Feedback Forms, QA Tools