## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Resources Required
TSK-001 | Project Requirements Gathering | Jane Smith | 2024-04-01 | 2024-04-15 | High | In Progress | Stakeholder Interviews, Documentation Tools
TSK-002 | System Design Finalization | Michael Chen | 2024-04-16 | 2024-05-05 | High | Planned | Design Software, UX Prototypes, Technical Reviews
TSK-003 | Development Phase - Backend Setup | Sarah Lee | 2024-05-06 | 2024-06-15 | Medium | Not Started | Servers, API Libraries, Database Schema
TSK-004 | User Testing & Feedback Loop | David Kim | 2024-06-16 | 2024-07-10 | High | Scheduled | Test Environment, Beta Users, Feedback Tools
TSK-005 | Deployment to Production | Team Lead | 2024-07-11 | 2024-07-15 | Critical | Pending Approval | Production Servers, Monitoring Tools, Backup Systems