## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Resources Required | Dependencies
T-001 | Project Kickoff Meeting | Team Lead | 2024-04-01 | 2024-04-03 | High | Planned | Conference Room, Project Manager, 1 PC | None
T-002 | Requirement Gathering Phase | Developer Team | <+2024-04-052024-05-15 | Medium | In Progress | Stakeholder Interviews, Documentation Tools | T-001
T-003 | UI/UX Design Review | Design Team | 2024-05-16 | 2024-05-31 | High | Planned | Design Software, Feedback Panel | T-002
T-004 | Backend Development Phase | Full Stack Developers | 2024-06-01 | 2024-07-15 | Critical | Not Started | Server Access, API Documentation, DB Tools | T-003
T-005 | Testing & Quality Assurance | QA Team | 2024-07-16 | 2024-08-15 | Medium | Planned | Test Environment, Automation Tools | T-004