## Worksheet
Task ID | Task Name | Assigned To | Priority | Start Date | End Date | Status | Duration (hrs) | Depends On | Notes
T001 | Project Planning Meeting | Jane Smith | High | 2024-04-01 | 2024-04-01 | In Progress | 2.5 | None | Review project scope and timelines.
T002 | Design Wireframes | John Doe | High | 2024-04-03 | 2024-04-10 | Not Started | 7.5 | T001 | Create initial UI mockups for login page.
T003 | Backend Development | Alex Kim | Critical | 2024-04-11 | 2024-05-05 | Scheduled | 35 | T002 | Develop API endpoints and database schema.
T004 | Frontend Integration | Sarah Lee | High | 2024-05-06 | 2024-05-15 | Not Started | 9 | T003 | Integrate frontend with backend APIs.
T005 | User Testing & Feedback | Team Lead | Medium | 2024-05-16 | 2024-05-31 | Planned | 15 | T004 | Conduct usability testing with beta users.