## Worksheet
Task ID | Task Name | Owner | Start Date | End Date th> | Status | Priority | Assigned To | Dependencies | Notes
T-001 | Project Kickoff Meeting | Sarah Johnson | 2024-04-01 | 2024-04-03 | In Progress | High | Project Team |  | Review project goals and timelines.
T-002 | Design Phase Finalization | Mike Chen | 2024-04-05 | 2024-04-15 | Pending | Medium | Design Team | T-001, T-003 | Finalize wireframes and user flows.
T-003 | Develop Backend API | Lena Park | 2024-04-10 | 2024-05-10 | Planned | High | Engineering Team | T-002 | Implement RESTful endpoints.
T-004 | User Testing Phase | David Ruiz | 2024-05-15 | 2024-05-30 | Not Started | Medium | QA Team | T-003, T-005 | Conduct usability tests with target users.