## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority | Estimated Hours | Progress (%)
T001 | Conduct Market Research | Sarah Johnson | 2024-04-01 | 2024-04-15 | In Progress | High | 10 | 65%
T002 | Develop Product Roadmap | David Lee | 2024-04-05 | 2024-04-25 | Pending | Medium | 8 | 0%
T003 | Client Presentation Draft | Lisa Chen | 2024-04-10 | 2024-04-20 | Not Started | High | 6 | 0%
T004 | Review Budget & Expenses | Michael Brown | 2024-04-12 | 2024-04-18 | Completed | Low | 3 | 100%