## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Duration (Days) | Dependencies | Notes
T001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | High | Completed | 0 | None | Initial planning session with stakeholders.
T002 | Requirement Gathering | Jane Smith | 2024-04-02 | 2024-04-15 | High | In Progress | 14 | T001 | Interviews with end users to collect functional needs.
T003 | Design Phase Finalization | Mike Johnson | 2024-04-16 | 2024-04-30 | Medium | Not Started | 15 | T002 | Finalize UI/UX mockups and get stakeholder approval.
T004 | Development Phase | Sarah Lee | 2024-05-01 | 2024-06-15 | High | Not Started | 60 | T003 | Code implementation based on approved design.
T005 | Testing & Quality Assurance | David Brown | 2024-06-16 | 2024-07-10 | High | Not Started | 35 | T004 | Functional and performance testing.
T006 | Deployment & Go-Live | Clara White | 2024-07-11 | 2024-07-15 | Medium | Not Started | 5 | T005 | Deploy to production environment.