## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Notes
T-001 | Design Brand Identity | Alex Johnson | 2024-04-01 | 2024-04-15 | In Progress | High | 80 | 45 | Final mockups due by April 10th.
T-002 | Develop Website Backend | Sara Patel | 2024-04-05 | 2024-05-10 | Pending | Medium | 120 | 0 | Waiting for API documentation.
T-003 | Client Onboarding Workshop | Jordan Lee | 2024-04-12 | 2024-04-13 | Completed | Low | 6 | 6 | All participants satisfied.
T-004 | Performance Optimization | Marcus Wong | 2024-05-01 | 2024-05-31 | Not Started | High | 40 | 0 | Target load time under 2s.
T-005 | Final Review & Delivery | Team Lead | 2024-06-15 | 2024-06-30 | In Progress | Critical | 30 | 15 | Must include all client feedback.