## Worksheet
Task ID | Task Name | Owner | Due Date | Priority | Status | Start Date | Estimated Hours | Progress (%) | Comments
TSK-001 | Project Kickoff Meeting | John Smith | 2024-04-15 | High | Completed | 2024-04-01 | 2.5 | 100% | No further action required.
TSK-002 | Design Final Prototypes | Sarah Lee | 2024-05-10 | Medium | In Progress | 2024-04-16 | 8 | 65% | Waiting for client feedback.
TSK-003 | Develop API Integration | Michael Chen | 2024-05-25 | High | Not Started | — | 12 | 0% | Requires backend team alignment.
TSK-004 | Client Training Session | Linda Wong | 2024-06-05 | Low | Planned | 2024-05-31 | 3.5 | 0% | To be scheduled with client.
TSK-005 | Final Testing & QA | David Kim | 2024-06-30 | High | Not Started | — | 15 | 0% | Depends on prototype completion.