## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Start Date | Estimated Hours | Progress (%) | Notes
T001 | Project Kickoff Meeting | John Smith | 2024-04-15 | High | Completed | 2024-04-10 | 2.5 | 100% | All team members present and aligned.
T002 | Design Wireframes | Sarah Lee | 2024-04-25 | Medium | In Progress | 2024-04-12 | 8 | 65% | Final review scheduled for April 23.
T003 | Develop Backend API | Mike Johnson | 2024-05-10 | High | Planned | 2024-04-18 | 15 | 0% | Waiting for database schema approval.
T004 | User Testing Phase | Linda Wong | 2024-05-30 | Low | Not Started | 2024-05-01 | 12 | 0% | Requires feedback from beta users.
T005 | Final Documentation | David Kim | 2024-06-10 | Medium | Scheduled | 2024-05-20 | 6 | 15% | Drafts ready for review by QA team.
Total Tasks |  |  |  |  | 5 | Summary Metrics