## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Start Date | Duration (Days) | Progress (%) | Notes
T001 | Project Kickoff Meeting | John Doe | 2023-10-05 | High | Completed | 2023-10-01 | 3 | 100%
T002 | Market Research Analysis | Jane Smith | 2023-10-15 | Medium | In Progress | 2023-10-03 | 7 | 65% | Needs feedback from Marketing Team.
T003 | UI/UX Design Finalization | Alex Chen | 2023-11-05 | High | Pending | 2023-10-10 | 14 | 0% | Waiting for client approval on wireframes.
T004 | Backend Development Phase | Mike Johnson | 2023-11-20 | High | Not Started | - | 30 | 0% | Requires API specifications from backend team.
T005 | QA Testing & Bug Fixes | Sarah Williams | 2023-12-05 | Medium | Planned | - | 10 | 0% | Scheduled after development completion.