## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (hrs) | Scheduled Time | Status | Priority | Notes
T001 | Finalize Project Proposal | John Doe | 2024-04-01 | 2024-04-15 | 16.5 | 9:00 AM - 5:30 PM | In Progress | High | Include market analysis and competitor review.
T002 | Design UI/UX Mockups | Jane Smith | 2024-04-05 | 2024-04-18 | 12 | 10:00 AM - 6:00 PM | Planned | Medium | Ensure accessibility compliance.
T003 | Conduct User Testing | Alex Chen | 2024-04-20 | 2024-04-25 | 8.5 | 9:30 AM - 3:30 PM | Scheduled | High | Recruit 15 participants from target group.
T004 | Prepare Financial Report | Sam Wilson | 2024-04-28 | 2024-05-03 | 15 | 8:00 AM - 7:30 PM | Pending Approval | Low | Submit to CFO for review.