## Worksheet
Task | Assigned To | Start Date | End Date | Scheduled Time (hrs) | Actual Time (hrs) | Status | Priority
Develop User Authentication Flow | Alex Morgan | 2024-04-01 | 2024-04-10 | 16 | 15 | Completed | High
Design Dashboard Interface | Samira Patel | 2024-04-11 | 2024-04-18 | 20 | 18 | In Progress | Medium
Integrate Payment Gateway | Jordan Lee | 2024-04-19 | 2024-05-03 | 32 | - | Planned | High
Conduct User Testing Sessions | Taylor Ruiz | 2024-05-04 | 2024-05-10 | 12 | 13 | Completed | Medium