## Worksheet
Task ID | Task Description | Assigned To | Due Date | Priority | Status | Estimated Hours | Start Date
T001 | Conduct market research for new product launch | Anna Smith | 2024-04-15 | High | In Progress | 10 | 2024-04-01
T002 | Finalize project timeline and milestones | James Lee | 2024-04-25 | Medium | Not Started | 8
T003 | Prepare budget proposal for Q2 | Lisa Chen | 2024-04-30 | High | Pending Review | 6 | 2024-04-05
T004 | Organize team workshop on agile practices | Robert Kim | 2024-05-10 | Low | Scheduled | 4 | 2024-05-01