## Worksheet
Week | Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority Level | Status | Resources Required | Budget Allocation ($) | Actual Spend ($) | Notes
Week 1 | TSK-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-01 |  | 1 | High | Completed | Conference Room, Zoom Access | 500 | 500 | Initial planning session held.
Week 2 | TSK-002 | Design Phase Review | John Doe | 2024-04-08 | 2024-04-15 | 5 | Medium | In Progress | Designer, Sketchbook, Design Tools | 1200 | 850 | Design drafts reviewed; feedback pending.
Week 3 | TSK-003 | Development Sprint Planning | Alice Johnson | 2024-04-22 | 2024-05-01 | 10 | High | Planned | Development Team, CI/CD Setup | 3500 | 0 | Sprint plan to be finalized in next week.
Week 4 | TSK-004 | QA Testing & Bug Fixes | Mark Wilson | 2024-05-05 | 2024-05-16 | 12 | High | Not Started | QA Tools, Test Cases, Bug Tracker | 2800 | 0 | Test environment ready for deployment.