## Worksheet
Week | Task Name | Assigned To | Start Date | End Date | Status | Priority | Resources Required | Budget (USD)
Week 1 | Project Kickoff Meeting | John Smith | 2023-10-02 | 2023-10-04 | In Progress | High | Conference Room, 1 Designer | $500
Week 2 | User Requirements Gathering | Sarah Lee | 2023-10-05 | 2023-10-11 | Pending Approval | High | Stakeholder Interviews, 3 Analysts | $4,200
Week 3 | UI/UX Design Phase | Mike Johnson | 2023-10-12 | 2023-10-18 | Planned | Moderate | Design Tools, 1 UI Lead | $3,500
Week 4 | Development Sprint Start | Emily Chen | 2023-10-19 | 2023-10-25 | Scheduled | High | Backend, 4 Developers, DevOps | $8,750
Week 5 | Quality Assurance Testing | David Wilson | 2023-10-26 | 2023-11-01 | Pending Start | Moderate | Test Environment, QA Team | $2,800
Total Budget (USD) | [6 empty] | $19,750