## Worksheet
Week | Task ID | Task Description |  |  | Assigned To | Start Date | End Date | Resources Required |  |  | Priority | Status
|  | Title | Duration (Days) | Dependencies |  |  |  | Personnel | Equipment | Budget (USD)
Week 1 | TS-001 | Project Kickoff Meeting | 5 |  | John Doe | 2024-04-01 | 2024-04-01 | Team Lead | 5 hours | None | High | Not Started
Week 1 | TS-002 | Requirements Gathering | 7 |  | Jane Smith, Alex Lee | 2024-04-02 | 2024-04-08 | Business Analysts | 15 hours | TS-001 | Medium | In Progress
Week 2 | TS-003 | Design Phase Review | 3 |  | Sarah Kim | 2024-04-09 | 2024-04-11 | UI/UX Designers | 8 hours |  | High | Scheduled
Week 3 | TS-004 | Development Sprint Start | 14 |  | Mike Johnson, Lisa Wong | 2024-04-12 | 2024-04-25 | Developers, DevOps | 35 hours | TS-002, TS-003 | Critical | Not Started
Week 4 | TS-005 | Testing and QA Review | 10 |  | David Brown, Emily Clark | 2024-04-26 | 2024-05-03 | QA Team, Test Tools | 25 hours | TS-004 | High | Planned
Week 5 | TS-006 | Final Deployment and Training | 7 |  | All Team Members | 2024-05-04 | 2024-05-11 | IT Support, Training Materials | 30 hours | TS-005 | Medium | Not Started
Total Tasks in This Schedule: 6 | [7 empty] | Estimated Total Hours: 170 |  |  | Budget Summary (USD): $450.00