## Worksheet
Week of | Task ID | Task Name | Assigned To | Start Date | End Date | Duration (hrs) | Priority | Status | Budget (USD)
April 7, 2024 – April 13, 2024 | TSK-001 | Project Kickoff Meeting | Jane Doe | Apr 7, 2024 | Apr 7, 2024 | 1.5 | High | Completed | 500
April 7, 2024 – April 13, 2024 | TSK-002 | Requirements Gathering | John Smith | Apr 8, 2024 | Apr 10, 2024 | 8 | High | In Progress | 1,200.00
April 7, 2024 – April 13, 2024 | TSK-003 | Design Phase Review | Sarah Lee | Apr 11, 2024 | Apr 12, 2024 | 3.5 | Medium | Scheduled | 600
April 7, 2024 – April 13, 2024 | TSK-004 | Development Setup | Mike Wong | Apr 13, 2024 | Apr 13, 2024 | 4 | Low | Pending | 300
April 7, 2024 – April 13, 2024 | TSK-005 | Testing Plan Drafting | Lisa Park | Apr 14, 2024 | Apr 15, 2024 | 6 | High | Not Started | 900
Total Budget for Week: |  |  |  | - | - | - | - | - | $3,500.00