## Worksheet
Date | Project Name | Team Member | Task Description | Estimated Hours | Actual Hours | Status | Priority Level | Deadline | Comments
2024-04-05 | Website Redesign | Sarah Johnson | Design wireframes for homepage and user dashboard | 8 | 6 | In Progress | High | 2024-04-15 | Wireframes approved by product manager on 04/05.
2024-04-06 | Mobile App Development | Michael Chen | Implement authentication module in React Native | 12 | 10 | In Progress | High | 2024-04-20 | Testing on Android devices completed.
2024-04-07 | Marketing Campaign | Lisa Rodriguez | Finalize ad creatives for social media platforms | 6 | 5 | Completed | Medium | 2024-04-07 | All creatives approved and scheduled for launch.
2024-04-08 | Internal Training Workshop | James Wilson | Conduct training session for new team members on tools | 4 | 4 | Completed | Low | 2024-04-08 | Attendance 95%. Feedback form collected.