## Worksheet
Project Name | Team Member | Task Description | Assigned Date | Due Date | Status | Estimated Cost | Actual Cost
Client Onboarding Initiative | Alex Rivera | Set up client portal and initial workflows | 03/15/2024 | 04/15/2024 | In Progress | $3,500 | $2,800
Product Launch Campaign | Jordan Lee | Coordinate cross-functional marketing and design team | 03/20/2024 | 05/10/2024 | Planned | $15,000 | $0
Team Performance Review | Taylor Chen | Conduct quarterly performance evaluations and feedback sessions | 04/01/2024 | 04/30/2024 | Completed | $1,200 | $1,200
User Support Integration | Morgan Patel | Integrate support tickets with CRM system | 03/30/2024 | 04/25/2024 | In Progress | $4,800 | $3,500