## Worksheet
Task ID | Team Member | Description | Assigned Date | Due Date | Status | Priority | Progress (%) | Comments
BT-001 | Alex Morgan | Finalize project scope document | 2023-10-05 | 2023-10-15 | In Progress | High | 65% | Need input from design team on deliverables.
BT-002 | Jordan Lee | Schedule team brainstorm session | 2023-10-06 | 2023-10-10 | Not Started | Medium | 0%
BT-003 | Taylor Reed | Review user feedback from beta test | 2023-10-07 | 2023-10-18 | In Progress | High | 40% | Highlight key usability issues in report.
BT-004 | Sam Patel | Prepare presentation for stakeholders | 2023-10-12 | 2023-10-25 | Not Started | High | 0%
BT-005 | Mia Chen | Coordinate cross-functional testing | 2023-10-14 | 2023-10-28 | Planned | Medium | 0%