## Worksheet
Date | Team Member | Task Description | Estimated Hours | Actual Hours | Status | Notes
2024-04-05 | Alice Johnson | Finalize project proposal draft | 8 | 7.5 | Completed | Submitted to team lead for review.
2024-04-06 | Bob Smith | Set up collaboration tools (Slack, Trello) | 4 | 4.2 | In Progress | Waiting for IT approval to finalize access.
2024-04-07 | Carol Lee | Organize weekly team meeting agenda | 2 | 2 | Completed | Agenda shared with all team members.
2024-04-08 | David Kim | Review team performance metrics | 6 | 5.8 | On Hold | Awaiting data from analytics platform.