## Worksheet
Budget Item | Team Member | Role | Responsibilities | Allocated Budget (USD) | Duration (Months) | Start Date | End Date | Status | Notes
Project Planning Workshop | John Smith | Project Manager | Lead planning sessions, define goals, assign tasks. | 2,500 | 1 | 2024-03-01 | 2024-03-31 | Completed | Included agile sprint setup.
Design Phase (UI/UX) | Sarah Lee | <+style="text-align:center;">UX DesignerCreate wireframes, user flows, prototypes. | 8,000 | 3 | 2024-04-01 | 2024-06-30 | In Progress | Client feedback scheduled in May.
Development Team (Backend) | Mike Johnson | Software Developer | Build APIs, database schema, integrate services. | 15,000 | 6 | 2024-07-01 | 2024-12-31 | Scheduled | Requires security compliance review.
Development Team (Frontend) | Emma Wong | Frontend Developer | Implement responsive UI, integrate with backend. | 12,000 | 6 | 2024-07-01 | 2024-12-31 | Scheduled | Must align with design deliverables.
Testing & QA Phase | David Kim | Quality Assurance Lead | Conduct functional, regression, and performance tests. | 4,500 | 4 | 2025-01-01 | 2025-04-30 | Pending | Testing environment to be provisioned.
Training & Onboarding | Linda Patel | Training Coordinator | Conduct onboarding for new team members and stakeholders. | 3,000 | 2 | 2025-05-01 | 2025-05-31 | Scheduled | Include documentation and Q&A sessions.