## Worksheet
Task | Responsible Person | Timeline (MM/YY) | Budget Allocation ($) | Status | Notes
Project Kickoff Meeting | Team Lead | 03/2024 | 500 | In Progress
Requirements Gathering | Product Owner | 04/2024 | 1,200.00 | Planned
Design Workshop | UX Designer | 05/2024 | 800 | Pending
Development Phase | Engineering Team | 06/2024 - 08/2024 | 5,000.00 | Not Started
QA & Testing | QA Manager | 09/2024 | 1,500.00 | Planned
Final Review & Launch | Team Lead | 10/2024 | 700 | Not Started