## Worksheet
Task | Owner | Assigned Date | Due Date | Estimated Hours | Actual Hours | Budget Allocation (USD) | Status | Notes
Project Kickoff Meeting | Sarah Johnson | 2024-03-15 | 2024-03-16 | 4 | 3.5 | 200 | Completed | All team members present and aligned on goals.
Requirement Gathering Workshop | Mark Lee | 2024-03-18 | 2024-03-20 | 8 | 7.5 | 400 | In Progress | Participants provided feedback; final document due by 21st.
UI/UX Design Finalization | Anna Patel | 2024-03-25 | 2024-04-01 | 16 | 14.5 | 800 | Planned | Design mockups reviewed by product team.
Development Sprint Planning | James Wong | 2024-04-03 | 2024-04-10 | 32 | - | 1600 | Not Started | Sprint goals and tasks to be finalized by 5th.
QA Testing Phase | Lisa Chen | 2024-04-15 | 2024-04-25 | 24 | - | 600 | Not Started | Testing environment ready by 18th.
Total Budget Allocated (USD) |  |  |  | - |  | 3000