## Worksheet
Activity | Responsible Team | Timeline | Budget Allocation (USD) | Status | Notes
Project Kickoff Meeting | Project Management Team | Week 1 - Day 1 | 500 | Planned | Finalize scope and roles.
Design Workshop Session | Design & UX Team | <Week 2 - Day 3 | 1,200 | In Progress | Collaborate on wireframes and user flows.
Development Sprint Planning | Engineering Team | Week 3 - Day 1 | 3,500 | Planned | Assign tasks and set milestones.
Client Review & Feedback | Client Relations Team | Week 4 - Day 5 | 800 | Scheduled | Gather input for final adjustments.
Final Quality Assurance Test | QA & Testing Team | Week 5 - Day 3 | 1,000 | Pending | Ensure all bugs are resolved.
Deployment & Go-Live | Operations & DevOps Team | Week 6 - Day 1 | 2,000 | Not Started | Monitor performance post-launch.