## Worksheet
Section | Key Objective | Team Roles & Responsibilities | Process Flow | Success Metrics | Timeline (Months) | Risks & Mitigation
1. Project Alignment | Ensure all team members understand strategic goals and project scope. | Project Manager – leads alignment sessions; Team Leads – provide domain insights. | Kick-off meeting → Goal mapping → Shared vision document. | 90% team clarity on project goals (measured via post-meeting survey). | Month 1 | Misalignment due to poor communication – mitigation: weekly check-ins and shared documentation.
2. Task Distribution | Assign clear, measurable tasks with ownership and deadlines. | Team Leads – assign tasks; Team Members – commit to deliverables. | Task planning → Assignment → Task tracking via project tool. | All tasks completed on time (95%+ completion rate). | Month 2–4 | Overloaded team members – mitigation: dynamic load balancing and weekly reviews.
3. Weekly Sync Meetings | Maintain regular communication to track progress and resolve blockers. | All team members – attend; Facilitator (Project Manager) – guides discussion. | Weekly meeting → Progress review → Action item assignment. | At least 80% of action items resolved by next meeting. | Month 1–6 | Meeting fatigue – mitigation: agenda pre-submission and time-boxing.
4. Decision Making | Establish transparent, collaborative processes for key decisions. | Team Leads – propose; Full team – vote or discuss; PM – finalizes. | Proposal → Discussion → Voting → Documentation. | All major decisions documented and approved within 2 business days. | Month 2–6 | Lack of consensus – mitigation: structured voting and facilitation training.
5. Feedback & Iteration | Create a culture of open feedback and continuous improvement. | Team members – provide input; PM – aggregates and acts on feedback. | Bi-weekly feedback session → Documentation → Action plan. | At least 3 actionable improvements per quarter. | Month 2–12 | Low engagement – mitigation: anonymous feedback tools and recognition incentives.
6. Knowledge Sharing | Ensure all team members have access to shared knowledge and best practices. | All members – contribute; Archivist – maintains repository. | Monthly knowledge sessions → Documentation upload → Review. | At least 5 new documents added monthly; team access rate ≥95%. | Month 1–12 | Poor documentation – mitigation: standardized templates and ownership assignment.