## Worksheet
Month | Team Objective | Key Activities | Responsible Members | Deadlines | Progress Status | Risks & Mitigations | Next Steps
January | Establish team onboarding process | Conduct team meeting, finalize roles, create communication plan | Project Manager, HR Lead | Jan 15 | Completed | No major risks identified. | Review documentation and share with department heads.
February | Develop quarterly goals and KPIs | Workshop with stakeholders, define success metrics | Team Leads, Strategy Officer | <Feb 20 | In Progress | Potential misalignment in KPI definition – to be resolved via cross-team review. | Finalize and present goals to executive team by Feb 25.
March | Implement agile sprints for project rollout | Sprint planning, weekly stand-ups, progress tracking | All Team Members | Mar 31 | Pending Start Date Confirmation | Unclear sprint duration – to be clarified with stakeholders. | Confirm sprint cadence and deliverables by March 10.
April | Evaluate team performance and adjust workflows | Review project outcomes, gather feedback, refine processes | Team Leads, HR Coordinator | Apr 15 | Planned | Potential resistance to change – mitigation via recognition and training. | Distribute performance summary to all members by Apr 12.