## Worksheet
Section | Objective | Key Activities | Responsibilities | Timeline | Success Metrics
1. Team Formation | Establish clear team roles and responsibilities. | Conduct initial team meetings, define core values, assign role matrices. | Project Manager, HR Representative, Department Heads | Week 1–2 | Team alignment score ≥85%, role clarity documented.
2. Goal Setting | Define measurable, SMART team objectives. | Workshop sessions, goal mapping, stakeholder input gathering. | Team Leads, Strategic Planning Officer | Week 3–4 | All goals approved by leadership; tracked in project management tool.
3. Daily Collaboration | Ensure consistent, productive communication. | Stand-up meetings, shared workspaces, feedback loops. | All Team Members | Ongoing (Daily) | 90% attendance in daily stand-ups; 100% participation in feedback sessions.
4. Weekly Reviews | Monitor progress and adjust strategies as needed. | Performance reviews, milestone tracking, action planning. | Project Manager, Team Leads | Every Week | All key milestones completed on time; no critical delays.
5. Conflict Resolution | Address and resolve team conflicts proactively.Conflict mediation sessions, root cause analysis, follow-up actions. | Team Manager, HR Support | As needed (within 72 hours) | No unresolved conflicts over 30 days; satisfaction score ≥80% in post-resolution survey.
6. Recognition & Feedback | Boost morale through recognition and constructive feedback. | Weekly appreciation sessions, peer reviews, anonymous feedback forms. | All Team Members | Ongoing | 100% participation in feedback; average satisfaction ≥4.5/5.