## Worksheet
Task | Owner | Due Date | Status | Progress (%) | Notes
Define project objectives | John Smith | 2024-03-15 | Completed | 100% | Finalized goals aligned with business strategy.
Identify key stakeholders | Emily Davis | 2024-03-20 | In Progress | 75% | Initial stakeholder list compiled; outreach in progress.
Develop collaboration framework | Michael Brown | 2024-03-25 | Pending | 30% | Draft version reviewed; finalizing meeting schedule.
Plan team meetings and check-ins | Sarah Lee | 2024-03-30 | Completed | 100% | Bi-weekly meeting calendar approved.
Set up communication tools | David Wong | 2024-03-28 | In Progress | 50% | Slack and Teams configured; training materials in draft.