## Worksheet
Week | Team Objective | Key Activities | Responsible Person(s) | Deadlines | Progress Status | Risks & Challenges | Next Steps
Week 1 | Establish core team communication channels | Set up Slack/Teams channels; schedule weekly sync meetings | Project Manager, Team Leads | Monday, April 8 | Completed | Initial resistance to digital tools from remote members | Conduct brief orientation session for new members
Week 2 | Define team goals and KPIs for Q2 | Conduct goal-setting workshop; align on performance metrics | Team Leads, HR Representative | Friday, April 19 | In Progress | Limited input from junior team members in planning phase | Invite all levels to contribute during next meeting
Week 3 | Complete sprint planning for product launch | Break down tasks; assign responsibilities; finalize timelines | Product Owner, Development Leads | Thursday, April 25 | On Track | Scope creep risk identified in initial draft | Add buffer time to critical path tasks
Week 4 | Conduct peer feedback roundtable | Facilitate anonymous feedback session; compile insights | HR & Team Lead Coordinator | Sunday, May 5 | Scheduled | Low participation due to scheduling conflicts | Send reminder and offer flexible time slots
Week 5 | Review Q2 performance and adjust goals | Analyze progress data; hold retrospective meeting | Project Manager, Analytics Lead | Friday, May 10 | Not Started | Unclear performance indicators for some teams | Define and standardize KPIs by end of week