## Worksheet
Quarter | Team Objective | Key Activities | Responsible Parties | Milestones & Deliverables | Performance Metrics | Risks & Mitigation
Q1 (Jan - Mar) | Establish team alignment and set annual goals | Team kickoff meeting, goal setting workshops, RACI matrix development | Project Manager, Team Leads | Finalized annual objectives; approved RACI chart | % of goals aligned with company strategy; team engagement score | Low participation — mitigate via early communication and incentives
Q2 (Apr - Jun) | Develop and execute core collaboration initiatives | Workflow optimization, cross-functional sprints, regular sync meetings | Collaboration Officers, Department Heads | Completed 3 pilot projects; documented process improvements | Project completion rate; meeting attendance and feedback scores | Resource constraints — mitigate via prioritization and agile planning
Q3 (Jul - Sep) | Scale successful practices across departments | Training sessions, tool rollout, feedback collection | HR & Training Team, Operations Managers | Launched collaboration platform; trained 100+ team members | Adoption rate of tools; satisfaction scores from training participants | Tool resistance — mitigate via peer champions and real-time support
Q4 (Oct - Dec) | Evaluate performance and plan for next year | Review meetings, success metrics analysis, strategic planning session | Executive Committee, Team Leaders | Final performance report; updated annual roadmap | Goal achievement rate; team satisfaction and innovation index | Lack of data visibility — mitigate via centralized dashboard implementation