## Worksheet
Task | Responsible Person | Deadline | Status | Notes
Define project goals and scope | Jane Smith | 2023-10-05 | Completed | Finalized with stakeholders.
Assign team roles and responsibilities | John Doe | 2023-10-10 | In Progress | Waiting for approval from HR.
Conduct first team meeting | Lisa Chen | 2023-10-15 | Pending | Agenda prepared and shared.
Set up communication channels | Michael Brown | 2023-10-08 | Completed | Email and Slack groups established.
Share project timeline and milestones | All Team Members | 2023-10-12 | Completed | Shared via team drive.