## Worksheet
Task | Assigned To | Due Date | Status | Progress (%) | Notes
Project Planning Meeting | Sarah Johnson | 2024-04-15 | Completed | 100% | All objectives defined and approved.
Design Wireframes | Mike Chen | 2024-04-22 | In Progress | 65% | Initial mockups ready; feedback pending.
Develop Backend API | Linda Patel | 2024-05-05 | Not Started | 0% | Awaiting design finalization.
User Testing Session | Team A | 2024-05-10 | Scheduled | 0% | To be conducted with QA team.
Final Review & Feedback | All Team Members | 2024-05-18 | Pending | 30% | Final edits and sign-off required.