## Worksheet
Date | Team Member | Activity Description | Responsible Role | Estimated Time (Hours) | Budget Allocated (USD) | Actual Cost (USD) | Status | Comments
2024-04-01 | Alex Morgan | Project Kickoff Meeting & Goal Setting | Team Lead | 2.5 | 500 | 500 | Completed
2024-04-05 | Jamie Lee | Requirements Gathering Workshop | Product Manager | 4 | 800 | 750 | Completed | Feedback incorporated from stakeholders.
2024-04-10 | Taylor Reed | Design Wireframes & User Flow Drafts | UI/UX Designer | 6 | 1200 | 1180 | Completed | Approved by Product Manager.
2024-04-15 | Jordan Patel | Frontend Development Setup | Senior Developer | 3.5 | 700 | 700 | Completed
2024-04-20 | Mia Chen | Backend API Integration Planning | Backend Engineer | 5 | 1000 | 1020 | Completed | Minor delays in third-party access.
2024-04-25 | Nate Walker | Team Retrospective & Feedback Session | Facilitator | 2 | 400 | 400 | Completed | Improvements noted in communication workflow.
Total Expenses |  |  |  | 28 | 5,600.00 | 5,370.00 | Budget Variance: -$230.00 (Under Budget)